## Sheet1
	NeoSofttech Website

		Working Status
Module	Pages/Component	WEB	Responsive	ETA
Index Module	Header Language Section	Done	Working
	Header Search	Done	Working
	Header Info	Done	Working
	Header Contact	Done	Working
	Header Who We Are Section	Done	Working
	Header What We Do	Done	Working
	Header We Work With	Done
	Header Technology	Done
	Who We Are Section in landing page	Done
	What We Do in Index page	Done
	Customer Section	Done
	Why Choose Us Section	Done
	Blogs	Done
	Full page JS PlugIn	Done
	Owl Carousel Plugin	Done
	footer Component	Done

Who We Are Module	OverView Componet(Main page)	One Section remaining		1day
	Competencies Componnet ( common )	One Section remaining		1day
	More About Component ( common )	One Section remaining		1day
	Industry Serve Component( common )	One Section remaining		1day
	overview Banner Componet( common )	One Section remaining		1day
	Mobile Application	One Section remaining		1day
	Web Development	One Section remaining		1day
	Cloud Computing	One Section remaining		1day
	AI & ML	One Section remaining		1day
	Analytics and Big Data	One Section remaining		1day
	Internet Of things	One Section remaining		1day
	Block Chain	One Section remaining		1day
	Dev Ops	One Section remaining		1day
	QA and Testing	One Section remaining		1day
	SAP	One Section remaining		1day
	UX/UI Design	One Section remaining		1day
	Software Consulting	One Section remaining		1day
	Internet Marketing	One Section remaining		1day

	End To End Product Eng			1day
	Enterprise Digital Transformation			1day
	Team Aumentation			1day

	Cometencies Section
	MicroSoft Tech ( 06 Pages)			6day
	Open Source Tech ( 18 pages)			6day
	Java Tech ( 5 pages)			5day
	Mobile Tech ( 6 pages)			7day
	Ux /Ui (7 pages)			7day
	Database Tech ( 2 pages)			4day
	CRM ( 4 pages )			5day
	Ecommerce Solution (5 pages)			5day
	CMS ( 5 pages)			5day
	ERP ( 2 pages )			2day
	Testing (01 pages)			1day
	Other (4 pagtes)			4day
	Clientite page(2 pages)			3day
	corporate facrt			1day
	Certification			1day
	Patners			1day
	Infrastructure			1day
	Global Present			1day
	CSR			1day
	Vision and Mission			1day
	Opertunity at neoSoft			1day
	Blog			1day
	Engagement Model			1day
	Devlopmet Model			1day

What We Do Module	Mobile Application			1day
	Web Development			1day
	Cloud Computing			1day
	AI & ML			1day
	Analytics and Big Data			1day
	Internet Of things			1day
	Block Chain			1day
	Dev Ops			1day
	QA and Testing			1day
	SAP			1day
	UX/UI Design			1day
	Software Consulting			1day
	Internet Marketing			1day
	End To End Product Eng			1day
	Enterprise Digital Transformation			1day
	Hire Now

We Work With Module	Enterprise			1day
	Agencies			1day
	Startups			1day
	banking And Finance			1day
	Ecommerce and Finance			1day
	Education learning			1day
	Gov and Semi gov			1day
	healthcar			1day
	Insurance			1day
	IT and Consulting			1day
	Manufacturing			1day
	Media and Entertainmnent			1day
	News and Publication			1day
	Startups			1day
	Telecoms			1day
				1day
Technology Module	Microsoft
	Open-Source			1day
	Java			1day
	Mobile			1day
	Frontend			1day
	DataBase			1day
	Big Data and Analytics			1day
	Internet Of things			1day
	Cloud Infrastructre			1day
	Block Chain			1day
	Dev Ops			1day
	SAP			1day
	AI & ML			1day
	CMS			1day
	CRM			1day
	CMS			1day
	ERP			1day

				3day
career				1day
Contact